## Sheet1
Item Name | Cost Date | Cost | Cumulative Cost
Project Start | 2021-04-29 | 0 | 0
PaintTech EasyDry Paint Booth (Deposit) | 2021-05-20 | 25000 | 25000
Facility Inspection Fee | 2021-05-27 | 1500 | 26500
Facility Prep (Electrical, HVAC) | 2021-05-27 | 5000 | 31500
LADBS Building Permit | 2021-06-14 | 500 | 32000
LADBS Electrical Permit | 2021-06-14 | 150 | 32150
LADBS Mechanical Permit | 2021-06-14 | 150 | 32300
LADBS Plumbing Permit | 2021-06-14 | 150 | 32450
LAFD Sprinkler Permit | 2021-06-14 | 1000 | 33450
SCAQMD Permit to Construct | 2021-06-14 | 1400 | 34850
SCAQMD Permit to Operate | 2021-06-14 | 1200 | 36050
PaintTech EasyDry Paint Booth (Remaining) | 2021-06-19 | 25000 | 61050
Equipment rentals (Boom lift, etc.) | 2021-06-20 | 1500 | 62550
Installation (Sprinklers, etc.) | 2021-06-22 | 5000 | 67550