## Sheet1
Module 2.3 - Visualizing the Budget - Instructions
1. Review the memos to identify updated costs, removed tasks, and any new requirements.
2. Revise the 2021 cost table with the new line items and amounts.
3. Assign costs to the appropriate dates based on your Gantt chart (e.g., deposits, permits, delivery, installation).
4. Update the cumulative totals in the table.
6. Create an updated Cost Baseline Diagram (cumulative cost curve) from your table.
7. (Bonus): Simplify the visual, highlight the key cost changes from 2021, and apply formatting that guides the viewer’s attention.
For tasks with ongoing costs (e.g., rentals, prep, installation), try spreading the total evenly across their duration instead of recording as a single lump sum.
2021 Cost Table
Item Name | Cost Date | Cost | Cumulative Cost
Project Start | 2021-04-29 | 0 | 0
PaintTech EasyDry Paint Booth (Deposit) | 2021-05-20 | 25000 | 25000
Facility Inspection Fee | 2021-05-27 | 1500 | 26500
Facility Prep (Electrical, HVAC) | 2021-05-27 | 5000 | 31500
LADBS Building Permit | 2021-06-14 | 500 | 32000
LADBS Electrical Permit | 2021-06-14 | 150 | 32150
LADBS Mechanical Permit | 2021-06-14 | 150 | 32300
LADBS Plumbing Permit | 2021-06-14 | 150 | 32450
LAFD Sprinkler Permit | 2021-06-14 | 1000 | 33450
SCAQMD Permit to Construct | 2021-06-14 | 1400 | 34850
SCAQMD Permit to Operate | 2021-06-14 | 1200 | 36050
PaintTech EasyDry Paint Booth (Remaining) | 2021-06-19 | 25000 | 61050
Equipment rentals (Boom lift, etc.) | 2021-06-20 | 1500 | 62550
Installation (Sprinklers, etc.) | 2021-06-22 | 5000 | 67550